## Slide 1
Stryker
AMS 3.0 Decommissioning Factory
Programme status · 27 May 2021
Overall status
On Track
SAVINGS REALISED
$3.2M
Achieved to date (as of May 2021)
DECOMMISSIONING PROGRESS
58 of 150 applications decommissioned (39%)
■ 58 Completed
■ 64 In progress
■ 4 On hold
■ 24 To be started
Key applications retired in May: SAP BW · Lotus Notes · Kronos
JUNE 2021 PLAN
18 apps to complete from the 64 in flight
Start the remaining 24 apps by 30 Jun 2021
Next up: SAP ECC 6.0, Siebel CRM, Oracle EBS 11i
RISKS & SERVICENOW
3
Risks identified
15
Tickets received
14
Closed (93%)
1
In progress
KEY RISKS & DEPENDENCIES
R1
4 apps on hold: business still uses them for operational reporting → owner review by 15 Jun, read-only archive option
R2
Archive sign-off for regulated apps pending with Compliance → weekly review, standard retention templates
R3
Business SME availability for SAP ECC data validation in June → slots booked 4 weeks ahead
D1
Infrastructure: archive storage capacity for next wave · due 15 Jun 2021
D2
Procurement: licence and contract exit notices to lock in savings
Foundation: training curriculum · onboarding · capacity planning · governance · trust & culture
Confidential
Notes: On Track. $3.2M savings realised to date. 58 of 150 decommissioned (39%); 64 in flight, 4 on hold, 24 not started. The 4 on-hold apps are the top risk: business stakeholders still use them for operational reporting. Key applications retired in May: SAP BW, Lotus Notes, Kronos (not the full list). June: complete 18, start the remaining 24 by 30 Jun. 3 risks open; 15 ServiceNow tickets received, 14 closed, 1 in progress. Figures other than those supplied, app names, risks and dependencies are samples.