## Slide 1
AMS 3.0 Decommissioning Factory 2021
Programme status · 27 May 2021
●
Overall status
On Track
SAVINGS REALISED
$3.2M
Achieved to date (as of May 2021)
DECOMMISSIONING PROGRESS
58 of 150 applications decommissioned (39%)
■ 58 Completed
■ 64 In progress
■ 4 On hold
■ 22 To be started
Key applications retired in May: SAP BW · Lotus Notes · Kronos
JUNE 2021 PLAN
18 apps to complete from the 64 in flight
Start the remaining 22 apps by 30 Jun 2021
Next up: SAP ECC 6.0, Siebel CRM, Oracle EBS 11i
RAID & Support Summary
3
Risks
14
Closed (93%)
1
In progress
KEY RISKS & DEPENDENCIES
R1
4 apps on hold: business still uses them for operational reporting → owner review by 15 Jun
R2
Archive sign-off for regulated apps pending with Compliance → weekly review
R3
Business SME availability for SAP ECC data validation in June → slots booked 4 weeks ahead
D1
Infrastructure: archive storage capacity for next wave · due 15 Jun 2021
D2
Procurement: licence and contract exit notices to lock in savings
Foundation: training curriculum · onboarding · capacity planning · governance · trust & culture
Confidential
2
Dependencies
3
Customer Escalations
15
Tickets
Notes: On Track. $3.2M savings realised to date. 58 of 150 decommissioned (39%); 64 in flight, 4 on hold, 24 not started. The 4 on-hold apps are the top risk: business stakeholders still use them for operational reporting. Key applications retired in May: SAP BW, Lotus Notes, Kronos. June: complete 18, start the remaining 24 by 30 Jun. 3 risks open; 15 ServiceNow tickets received, 14 closed, 1 in progress.
1

## Slide 2
Decommissioning: overall status and plan
150 apps in scope — 58 Completed (40%), 35 – In progress, 197 planned to be completed in the next 6 months
Confidential
150
In scope
58
Completed (39%)
64
In progress
4
On hold
24
To be started
By complexity
Apps by status within each complexity tier
Chart: 
| Simple | Medium | Complex
Completed | 38 | 16 | 4
In progress | 24 | 26 | 14
On hold | 0 | 1 | 3
To be started | 8 | 7 | 9
Complex apps: 4 of 30 done (13%) — the long tail of the plan
Chart: Apps remaining
| Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021
Retired | 87 | 78 | 69 | 61 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retired + Data Archival | 55 | 50 | 45 | 41 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned – Retired | 0 | 0 | 0 | 0 | 0 | 42 | 32 | 24 | 14 | 6 | 0 | 0
Planned – Retired + Data Archival | 0 | 0 | 0 | 0 | 0 | 28 | 22 | 16 | 10 | 4 | 0 | 0
On hold | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Today

## Slide 3
Open risks and challenges
Priority, probability and mitigation plan
# | Risk / challenge | Priority | Probability | Mitigation plan | Owner
R1 | Infrastructure: archive storage capacity for next wave · due 15 Sep | High | High (70%) | Archive storage capacity for next wave · due 15 Sep | 
R2 | Procurement: licence and contract exit notices to lock in savings | High | Medium (50%) | Joint readiness checkpoint with platform team; re-sequence apps not dependent on platform | 
R3 | Apps on Hold | High | High (65%) | Finalise retention policy; agree retrieval SLA; validate with sample restores; connects with respective owners planned | 
R4 | Undocumented app dependencies cause post-shutdown incidents | Medium | Medium (40%) | Dependency scan before cutover; read-only period before final shutdown | 
R5 | Vendor licence notice periods delay cost savings | Medium | Medium (45%) | Track notice dates; raise terminations early with procurement | 
R6 | SME availability for legacy apps reduces | Low | Low (25%) | Capture knowledge in runbooks; book SME time in advance | 
Confidential

## Slide 4
Customer Escalations
3 open escalations requiring leadership attention
5 apps need to be retired early.
Raised by: cccc
Business is concerned about keeping 5 apps active until next wave due to infrastructure costs and wants reprioritization.
Ask: Align on wave sequencing and reprioritize
Target: 10 Sep
Open
Retrieval SLA for archived data
Raised by: gggg
Compliance wants guaranteed retrieval times and retention periods before apps are shut down.
Ask: Confirm SLA and retention policy
Target: 15 Sep
In progress
Self Serve reporting workbench erratic behavior
Raised by: Aaaaa
Users reported slowness, blank results and page error while running reports
Ask: Platform team installed patch
Target: 20 Sep
Closed
Confidential

## Slide 5
SNOW at a glance
15
Tickets received
14
Closed (93%)
1
In progress
# | Ticket / request | Category | Priority | Status | Opened | Resolution / next step | Owner
 | [INC/RITM no.] – [short description] | [Category] | [P1–P4] | In progress | [dd Mon] | [Current action and expected close date] | [Name]
 | [INC/RITM no.] – [short description] | [Category] | [P1–P4] | Closed | [dd Mon] | [How it was resolved] | [Name]
 | [INC/RITM no.] – [short description] | [Category] | [P1–P4] | Closed | [dd Mon] | [How it was resolved] | [Name]
 | [INC/RITM no.] – [short description] | [Category] | [P1–P4] | Closed | [dd Mon] | [How it was resolved] | [Name]
 | [INC/RITM no.] – [short description] | [Category] | [P1–P4] | Closed | [dd Mon] | [How it was resolved] | [Name]