## Gantt
CJA Customer Insight Backend Views – Project Plan
Project start (Monday): |  | 2026-10-05 | Go-live: | 2026-11-24
ID | Phase / Task | Owner (role) | Type | Start offset (wd) | Duration (wd) | Start | End | Depends on | Status | % Complete | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
[11 empty] | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23
0 | Mobilisation & Governance |  | Phase | 0 | 7 | 2026-10-05 | 2026-10-13 |  |  | 0%
0.1 | Kickoff, stakeholder map, RACI | PM | Task | 0 | 2 | 2026-10-05 | 2026-10-06 |  | Not started | 0%
0.2 | Databricks workspace / Unity Catalog + source-system access requests | Platform / DevOps | Task | 0 | 7 | 2026-10-05 | 2026-10-13 | 0.1 | Not started | 0%
0.3 | Governance cadence set up (weekly status, steering) | PM | Task | 2 | 3 | 2026-10-07 | 2026-10-09 | 0.1 | Not started | 0%
M0 | Kickoff complete | PM | Milestone | 1 | 0 | 2026-10-06 | 2026-10-06 | 0.1 | Not started | 0% | bar: 2026-10-05
1 | Requirements & Data Analysis (iterative, by batch) |  | Phase | 0 | 20 | 2026-10-05 | 2026-10-30 |  |  | 0%
1.1 | Batch A (~20 attrs, internal sources) – requirements & definitions | BA / Business SME | Task | 0 | 5 | 2026-10-05 | 2026-10-09 | 0.1 | Not started | 0%
1.2 | Batch A – source mapping, profiling, DQ assessment | Data Analyst | Task | 2 | 8 | 2026-10-07 | 2026-10-16 | 1.1 | Not started | 0%
M1A | Batch A requirements + analysis sign-off | Business SME | Milestone | 9 | 0 | 2026-10-16 | 2026-10-16 | 1.2 | Not started | 0% | bar: 2026-10-12
1.3 | Batch B (~20 attrs, derived / multi-source) – requirements | BA / Business SME | Task | 3 | 7 | 2026-10-08 | 2026-10-16 | 0.1 | Not started | 0%
1.4 | Batch B – source mapping, profiling, DQ assessment | Data Analyst | Task | 5 | 10 | 2026-10-12 | 2026-10-23 | 1.3 | Not started | 0%
M1B | Batch B requirements + analysis sign-off | Business SME | Milestone | 14 | 0 | 2026-10-23 | 2026-10-23 | 1.4 | Not started | 0% | bar: 2026-10-19
1.5 | Batch C (~10 attrs, third-party / ambiguous) – requirements | BA / Business SME | Task | 5 | 10 | 2026-10-12 | 2026-10-23 | 0.1 | Not started | 0%
1.6 | Batch C – source mapping, profiling (needs 3P sample) | Data Analyst | Task | 12 | 8 | 2026-10-21 | 2026-10-30 | 1.5, 2.2 | Not started | 0%
1.7 | Customer identity / key-stitching analysis across sources | Data Architect | Task | 3 | 9 | 2026-10-08 | 2026-10-20 | 1.1 | Not started | 0%
1.8 | Gap list: unsourced / partial attributes – resolution | BA / Data Analyst | Task | 5 | 15 | 2026-10-12 | 2026-10-30 | 1.2 | Not started | 0%
M1R | Requirements baseline gate (Batch C conditional) | PM / Business SME | Milestone | 14 | 0 | 2026-10-23 | 2026-10-23 | M1A, M1B | Not started | 0% | bar: 2026-10-19
M1C | Batch C sign-off | Business SME | Milestone | 19 | 0 | 2026-10-30 | 2026-10-30 | 1.6 | Not started | 0% | bar: 2026-10-26
2 | Third-Party Dependency Track (critical path) |  | Phase | 0 | 30 | 2026-10-05 | 2026-11-13 |  |  | 0%
2.1 | Interface spec agreed (fields, format, frequency, keys, SLA) | PM / Third party | Task | 0 | 10 | 2026-10-05 | 2026-10-16 | 0.1 | Not started | 0%
M2S | 3P interface spec signed | Third party | Milestone | 9 | 0 | 2026-10-16 | 2026-10-16 | 2.1 | Not started | 0% | bar: 2026-10-12
2.2 | Sample data received & analysed | Third party / Data Analyst | Task | 10 | 5 | 2026-10-19 | 2026-10-23 | 2.1 | Not started | 0%
2.3 | Test feed delivered & validated | Third party / Data Engineer | Task | 15 | 5 | 2026-10-26 | 2026-10-30 | 2.2 | Not started | 0%
M2F | Fallback decision: descope / stub 3P attrs if test feed not validated | Steering | Milestone | 19 | 0 | 2026-10-30 | 2026-10-30 | 2.3 | Not started | 0% | bar: 2026-10-26
2.4 | Production feed setup & first delivery | Third party / Data Engineer | Task | 25 | 5 | 2026-11-09 | 2026-11-13 | 2.3 | Not started | 0%
M2P | 3P production feed live | Third party | Milestone | 29 | 0 | 2026-11-13 | 2026-11-13 | 2.4 | Not started | 0% | bar: 2026-11-09
3 | Design & Business Rules |  | Phase | 5 | 20 | 2026-10-12 | 2026-11-06 |  |  | 0%
3.1 | Target model (bronze / silver / gold) & curated view design standards | Data Architect | Task | 5 | 7 | 2026-10-12 | 2026-10-20 | 1.1 | Not started | 0%
3.2 | Batch A – source-to-target mapping (STTM) & business rules | Data Architect / BA | Task | 7 | 8 | 2026-10-14 | 2026-10-23 | 1.2 | Not started | 0%
3.3 | Batch B – STTM & business rules | Data Architect / BA | Task | 12 | 8 | 2026-10-21 | 2026-10-30 | 1.4 | Not started | 0%
3.4 | Batch C – STTM & business rules | Data Architect / BA | Task | 17 | 8 | 2026-10-28 | 2026-11-06 | 1.6 | Not started | 0%
3.5 | Business rule review & approval (rolling) | Business SME | Task | 12 | 13 | 2026-10-21 | 2026-11-06 | 3.2 | Not started | 0%
M3 | Design sign-off (all batches) | Data Architect / Business SME | Milestone | 24 | 0 | 2026-11-06 | 2026-11-06 | 3.4, 3.5 | Not started | 0% | bar: 2026-11-02
4 | Integration & Build |  | Phase | 5 | 25 | 2026-10-12 | 2026-11-13 |  |  | 0%
4.1 | Env setup: catalogs, schemas, permissions, CI/CD (Asset Bundles) | Platform / DevOps | Task | 5 | 10 | 2026-10-12 | 2026-10-23 | 0.2 | Not started | 0%
4.2 | Batch A – ingestion to bronze, conform to silver | Data Engineer | Task | 12 | 8 | 2026-10-21 | 2026-10-30 | 3.2, 4.1 | Not started | 0%
4.3 | Batch A – gold curated views | Data Engineer | Task | 15 | 5 | 2026-10-26 | 2026-10-30 | 4.2 | Not started | 0%
4.4 | Batch B – ingestion to bronze, conform to silver | Data Engineer | Task | 17 | 8 | 2026-10-28 | 2026-11-06 | 3.3 | Not started | 0%
4.5 | Batch B – gold curated views | Data Engineer | Task | 20 | 5 | 2026-11-02 | 2026-11-06 | 4.4 | Not started | 0%
4.6 | Batch C – third-party ingestion to bronze / silver | Data Engineer | Task | 22 | 8 | 2026-11-04 | 2026-11-13 | 3.4, 2.3 | Not started | 0%
4.7 | Batch C – gold curated views | Data Engineer | Task | 25 | 5 | 2026-11-09 | 2026-11-13 | 4.6 | Not started | 0%
4.8 | Orchestration (Workflows / Jobs) & DQ expectations | Data Engineer | Task | 20 | 10 | 2026-11-02 | 2026-11-13 | 4.2 | Not started | 0%
M4 | Build complete | Data Engineering Lead | Milestone | 29 | 0 | 2026-11-13 | 2026-11-13 | 4.7, 4.8 | Not started | 0% | bar: 2026-11-09
5 | Testing |  | Phase | 15 | 20 | 2026-10-26 | 2026-11-20 |  |  | 0%
5.1 | Unit testing (rolling, per batch) | Data Engineer | Task | 15 | 15 | 2026-10-26 | 2026-11-13 | 4.2 | Not started | 0%
5.2 | SIT – Batch A | QA | Task | 20 | 5 | 2026-11-02 | 2026-11-06 | 4.3 | Not started | 0%
5.3 | SIT – Batch B & C | QA | Task | 25 | 8 | 2026-11-09 | 2026-11-18 | 4.5, 4.7 | Not started | 0%
5.4 | Source-to-target reconciliation | QA / Data Analyst | Task | 22 | 11 | 2026-11-04 | 2026-11-18 | 5.2 | Not started | 0%
5.5 | Performance & refresh-SLA testing | QA / Data Engineer | Task | 28 | 5 | 2026-11-12 | 2026-11-18 | 4.8 | Not started | 0%
5.6 | Defect triage & fixes | Data Engineer | Task | 22 | 13 | 2026-11-04 | 2026-11-20 | 5.2 | Not started | 0%
M5 | SIT exit | QA Lead | Milestone | 32 | 0 | 2026-11-18 | 2026-11-18 | 5.3, 5.4, 5.5 | Not started | 0% | bar: 2026-11-16
6 | UAT |  | Phase | 25 | 10 | 2026-11-09 | 2026-11-20 |  |  | 0%
6.1 | UAT prep: scripts, test data, CJA test connection | QA / BA | Task | 25 | 8 | 2026-11-09 | 2026-11-18 | 4.5 | Not started | 0%
6.2 | Business validation of all 50 attributes | Business SME | Task | 30 | 5 | 2026-11-16 | 2026-11-20 | 6.1, M5 | Not started | 0%
6.3 | CJA end-to-end ingestion test | CJA Admin / Data Engineer | Task | 30 | 5 | 2026-11-16 | 2026-11-20 | 6.1 | Not started | 0%
6.4 | UAT defect fixes | Data Engineer | Task | 31 | 4 | 2026-11-17 | 2026-11-20 | 6.2 | Not started | 0%
M6 | UAT sign-off | Business SME | Milestone | 34 | 0 | 2026-11-20 | 2026-11-20 | 6.2, 6.3, 6.4 | Not started | 0% | bar: 2026-11-16
7 | Deployment & Hypercare |  | Phase | 32 | 8 | 2026-11-18 | 2026-11-27 |  |  | 0%
7.1 | Runbook, support model, handover | Data Engineer / Support | Task | 32 | 5 | 2026-11-18 | 2026-11-24 | M5 | Not started | 0%
7.2 | Prod deployment (Asset Bundles) & CJA prod connection | Platform / DevOps | Task | 35 | 2 | 2026-11-23 | 2026-11-24 | M6 | Not started | 0%
M7G | Go-live | PM | Milestone | 36 | 0 | 2026-11-24 | 2026-11-24 | 7.2 | Not started | 0% | bar: 2026-11-23
7.3 | Hypercare | Data Engineer / Support | Task | 36 | 4 | 2026-11-24 | 2026-11-27 | M7G | Not started | 0%
M7C | Project close | PM | Milestone | 39 | 0 | 2026-11-27 | 2026-11-27 | 7.3 | Not started | 0% | bar: 2026-11-23
How to use
• Yellow cell C3 = project start (must be a Monday). All dates are formulas off it.
• Blue numbers (Start offset / Duration, in working days) are the inputs. Edit these to move a task; Start/End recalculate.
• Update Status and % Complete (cream cells) weekly. Tasks at 100% turn grey on the timeline. Phase % is duration-weighted.
• ◆ = milestone / gate. The current week is highlighted yellow in the header.
• Assumptions: Mon–Fri working days, no public holidays loaded; batch split A≈20 / B≈20 / C≈10 attributes is a placeholder – see Attribute Tracker.
• Critical path: 3P interface spec (W2) → test feed (W4) → Batch C build (W5–W6). Fallback decision at end W4 is non-negotiable to hold go-live.
Formulas:
Duration (wd) = NETWORKDAYS([Start],[End])
Start = MIN([Start, row below]:G10)
Start = WORKDAY(C2,[Start offset (wd)])
End = MAX([End, row below]:H10)
End = WORKDAY([Start],[Duration (wd)]-1)
Note on C2: Input. Change this and every date in the plan shifts. Must be a Monday. Assumed 5-Oct-2026.

## Milestones
Milestones & Gates
ID | Milestone / Gate | Owner | Date | Week | Status | Days to go
M0 | Kickoff complete | PM | 2026-10-06 | W1 | Not started | 4
M1A | Batch A requirements + analysis sign-off | Business SME | 2026-10-16 | W2 | Not started | 12
M1B | Batch B requirements + analysis sign-off | Business SME | 2026-10-23 | W3 | Not started | 17
M1R | Requirements baseline gate (Batch C conditional) | PM / Business SME | 2026-10-23 | W3 | Not started | 17
M1C | Batch C sign-off | Business SME | 2026-10-30 | W4 | Not started | 22
M2S | 3P interface spec signed | Third party | 2026-10-16 | W2 | Not started | 12
M2F | Fallback decision: descope / stub 3P attrs if test feed not validated | Steering | 2026-10-30 | W4 | Not started | 22
M2P | 3P production feed live | Third party | 2026-11-13 | W6 | Not started | 32
M3 | Design sign-off (all batches) | Data Architect / Business SME | 2026-11-06 | W5 | Not started | 27
M4 | Build complete | Data Engineering Lead | 2026-11-13 | W6 | Not started | 32
M5 | SIT exit | QA Lead | 2026-11-18 | W7 | Not started | 35
M6 | UAT sign-off | Business SME | 2026-11-20 | W7 | Not started | 37
M7G | Go-live | PM | 2026-11-24 | W8 | Not started | 39
M7C | Project close | PM | 2026-11-27 | W8 | Not started | 42
All cells link to the Gantt sheet (green) – update status there.
Formulas:
Days to go = IF([Status]="Done","-",NETWORKDAYS(TODAY(),[Date])-1)

## Attribute Tracker
Attribute Tracker – 50 CJA attributes
Fill one row per business attribute. Row 1 is a worked example (replace it). Yellow = drop-down status columns.
Progress summary (count of attributes = Done)
Batch | Requirements | Data analysis | Design | Build | SIT | UAT | Total attrs
A | 1 | 0 | 0 | 0 | 0 | 0 | 20
B | 0 | 0 | 0 | 0 | 0 | 0 | 20
C | 0 | 0 | 0 | 0 | 0 | 0 | 10
Total | 1 | 0 | 0 | 0 | 0 | 0 | 50
# | Attribute name | Business definition | Batch | Grain | Source system(s) | Source table.field | 3P dependent? | Business rule / derivation | Target view | Requirements | Data analysis | Design | Build | SIT | UAT | Owner | Comments
1 | Last purchase date | Date of the customer's most recent completed order | A | Customer | Order Management (OMS) | oms.orders.order_ts | N | MAX(order_ts) WHERE order_status = 'COMPLETED', per customer_id | gold.v_cja_customer_profile | Done | In progress | Not started | Not started | Not started | Not started | BA – TBD | Example row – replace
2 | Attribute 02 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
3 | Attribute 03 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
4 | Attribute 04 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
5 | Attribute 05 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
6 | Attribute 06 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
7 | Attribute 07 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
8 | Attribute 08 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
9 | Attribute 09 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
10 | Attribute 10 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
11 | Attribute 11 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
12 | Attribute 12 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
13 | Attribute 13 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
14 | Attribute 14 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
15 | Attribute 15 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
16 | Attribute 16 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
17 | Attribute 17 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
18 | Attribute 18 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
19 | Attribute 19 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
20 | Attribute 20 |  | A |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
21 | Attribute 21 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
22 | Attribute 22 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
23 | Attribute 23 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
24 | Attribute 24 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
25 | Attribute 25 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
26 | Attribute 26 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
27 | Attribute 27 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
28 | Attribute 28 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
29 | Attribute 29 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
30 | Attribute 30 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
31 | Attribute 31 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
32 | Attribute 32 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
33 | Attribute 33 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
34 | Attribute 34 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
35 | Attribute 35 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
36 | Attribute 36 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
37 | Attribute 37 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
38 | Attribute 38 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
39 | Attribute 39 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
40 | Attribute 40 |  | B |  |  |  | TBC |  |  | Not started | Not started | Not started | Not started | Not started | Not started
41 | Attribute 41 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
42 | Attribute 42 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
43 | Attribute 43 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
44 | Attribute 44 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
45 | Attribute 45 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
46 | Attribute 46 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
47 | Attribute 47 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
48 | Attribute 48 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
49 | Attribute 49 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started
50 | Attribute 50 |  | C |  |  |  | Y |  |  | Not started | Not started | Not started | Not started | Not started | Not started

## RAID Log
RAID Log – Risks, Assumptions, Issues, Dependencies
ID | Type | Description | Impact | Likelihood | Owner | Mitigation / action | Due (week) | Status
R1 | Risk | Third-party feed (spec, sample, test feed) slips past W4, blocking Batch C build | High | High | PM | Contractual dates for spec/sample/test feed; weekly 3P checkpoint; fallback decision at end W4 (descope or stub Batch C attrs) | W4 | Open
R2 | Risk | Source-system and Databricks/UC access requests take longer than 1 week | High | Medium | Platform / DevOps | Raise all access requests on day 1; named approver per source; escalate at W1 steering | W1 | Open
R3 | Risk | Attribute definitions change after batch sign-off, forcing rework | Medium | Medium | BA | Batch sign-off baseline; change requests assessed against go-live date | W3 | Open
R4 | Risk | Customer identity keys don't reconcile across sources, lowering match rate | High | Medium | Data Architect | Identity-stitching analysis in W1–W2; agree survivorship / match rules early | W2 | Open
R5 | Risk | Business SMEs not available for UAT in W7 | Medium | Medium | PM | Book UAT testers and slots by W3 | W3 | Open
A1 | Assumption | CJA consumes the Databricks curated views via an agreed connector/export pattern (to be confirmed in W1) | High | - | Data Architect | Confirm integration pattern & refresh SLA with CJA admin | W1 | Open
A2 | Assumption | 50-attribute scope is fixed; additions go through change control | Medium | - | PM | Scope baseline at requirements gate | W3 | Open
A3 | Assumption | Non-prod environments mirror prod closely enough for SIT/UAT | Medium | - | Platform / DevOps | Validate env parity during 4.1 | W3 | Open
D1 | Dependency | Third party provides interface spec (W2), sample (W3), test feed (W4), prod feed (W6) | High | - | Third party | Tracked in Gantt section 2 | W6 | Open
D2 | Dependency | Source-system owners provide access and SMEs for profiling | High | - | PM | Named contact per source system | W1 | Open